## Sheet8
task | status | pos | start | end
Check out library book | done | 0thWeek_1 | 2017-11-13 | 14d
Renew library book | done | 0thWeek_2 | 2017-11-27 | 14d
Design Your Plan for Writing | critical | 1stWeek_0 | 2017-12-05 | 7d
Instruction:Understanding feelings about writing. | active | 1stWeek_1 | 2017-12-05 | 2d
Instruction:Keys to positive writing experiences. | active | 1stWeek_2 | after 1stWeek_1 | 2d
Instruction: Designing a plan for submitting your article in 12 weeks. | active | 1stWeek_3 | after 1stWeek_2 | 3d
Exercises: Selecting a paper of revision. | active | 1stWeek_a | 2017-12-05 | 2d
Exercises: Choosing your writing site. | active | 1stWeek_b | after 1stWeek_a | 1d
Exercises: Designing your writing schedule. | active | 1stWeek_c | after 1stWeek_b | 2d
Exercises: Anticipating and overturning writing obstacles. | active | 1stWeek_d | after 1stWeek_c | 2d
Starting Your Article | critical | 2ndWeek_0 | after 1stWeek_0 | 7d
Instruction: Types of academic articles. | active | 2ndWeek_1 | after 1stWeek_3 | 1d
Instruction: Myths about publishable journal articles. | active | 2ndWeek_2 | after 2ndWeek_1 | 1d
Instruction: What gets published and why. | active | 2ndWeek_3 | after 2ndWeek_2 | 1d
Instruction: Abstracts as a tool for success. | active | 2ndWeek_4 | after 2ndWeek_3 | 2d
Instruction: Getting started on your article revision. | active | 2ndWeek_5 | after 2ndWeek_4 | 2d
Exercise: Hammering out your topic. | active | 2ndWeek_a | after 1stWeek_d | 1d
Exercise: Rereading your paper. | active | 2ndWeek_b | after 2ndWeek_a | 1d
Exercise: Drafting your abstract. | active | 2ndWeek_c | after 2ndWeek_b | 2d
Exercise: Reading a model article. | active | 2ndWeek_d | after 2ndWeek_c | 1d
Exercise: Revising your abstract. | active | 2ndWeek_e | after 2ndWeek_d | 2d
Advancing Your Argument | critical | 3rdWeek_0 | after 2ndWeek_0 | 7d
Instruction: Common reasons why journals reject articles. | active | 3rdWeek_1 | after 2ndWeek_e | 1d
Instruction: Main reason journal articles are rejected: no argument. | active | 3rdWeek_2 | after 3rdWeek_1 | 1d
Instruction: Making a good argument. | active | 3rdWeek_3 | after 3rdWeek_2 | 2d
Instruction: Organizing your article around your argument. | active | 3rdWeek_4 | after 3rdWeek_3 | 3d
Exercise: Drafting your argument. | active | 3rdWeek_a | after 2ndWeek_e | 3d
Exercise: Reviewing your article for an argument. | active | 3rdWeek_b | after3rdWeek_a | 2d
Exercise: Revising your article around your argument. | active | 3rdWeek_c | after 3rdWeek_b | 2d
Selecting a Journal | critical | 4thWeek_0 | after 3rdWeek_0 | 7d
Instruction: Good news about journals. | active | 4thWeek_1 | after 3rdWeek_4 | 1d
Instruction: The importance of picking the right journal. | active | 4thWeek_2 | after 4thWeek_1 | 1d
Instruction: Types of academic journals; nonrecommended, questionable, and preferred. | active | 4thWeek_3 | after 4thWeek_2 | 2d
Instruction: Finding suitable academic journals. | active | 4thWeek_4 | after 4thWeek_3 | 3d
Exercise: Searching for journals. | active | 4thWeek_a | after 3rdWeek_d | 1d
Exercise: Evaluating acedemic journals. | active | 4thWeek_b | after 4thWeek_a | 1d
Exercise: Matching your article to suitable journals. | active | 4thWeek_c | after 4thWeek_b | 1d
Exercise: Reading relevant journals. | active | 4thWeek_d | after 4thWeek_c | 2d
Exercise: Writing a query letter to editors. | active | 4thWeek_e | after 4thWeek_d | 1d
Exercise: Making a final decision about which journal. | active | 4thWeek_f | after 4thWeek_e | 1d
Reviewing the Related Literature | critical | 5thWeek_0 | after 4thWeek_0 | 7d
Instruction: Reading the scholarly literatures. | active | 5thWeek_1 | after 4thWeek_4 | 1d
Instruction: Types of scholarly literature. | active | 5thWeek_2 | after 5thWeek_1 | 1d
Instruction: Strategies for getting reading done. | active | 5thWeek_3 | after 5thWeek_2 | 1d
Instruction: Identifying your relationship to the related literature. | active | 5thWeek_4 | after 5thWeek_3 | 1d
Instruction: Avoiding plagiarism. | active | 5thWeek_5 | after 5thWeek_4 | 1d
Instruction: Writing about others' research. | active | 5thWeek_6 | after 5thWeek_5 | 2d
Exercise: Evaluating your current conditions. | active | 5thWeek_a | after 4thWeek_f | 1d
Exercise: Identifying and reading the related literature. | active | 5thWeek_b | after 5thWeek_a | 2d
Exercise:Evaluating the related literature. | active | 5thWeek_c | after 5thWeek_b | 2d
Exercise: Writing or revisiting your related literature review. | active | 5thWeek_d | after 5thWeek_c | 2d
Strengthing Your Structure | critical | 6thWeek_0 | after 5thWeek_0 | 7d
Instruction: On the importance of structure. | active | 6thWeek_1 | after 5thWeek_6 | 1d
Instruction: Types of structures. | active | 6thWeek_2 | after 6thWeek_1 | 1d
Instruction: Article structures in the social sciences and humanities. | active | 6thWeek_3 | after 6thWeek_2 | 2d
Instruction: Solving structural problems. | active | 6thWeek_4 | after 6thWeek_3 | 3d
Instruction: Revising for structure. | active | 6thWeek_5 | after 6thWeek_4
Exercise: Outlining a model article. | active | 6thWeek_a | after 5thWeek_d | 1d
Exercise: Outlining your article. | active | 6thWeek_b | after 6thWeek_a | 1d
Exercise: Restructuring your article. | active | 6thWeek_c | after 6thWeek_b | 1d
Presenting Your Evidence | critical | 7thWeek_0 | after 6thWeek_0 | 7d
Instruction: Types of evidence. | active | 7thWeek_1 | after 6thWeek_5 | 1d
Instruction: Writing up evidence in the social sciences. | active | 7thWeek_2 | after 7thWeek_1 | 1d
Instruction: Writing up evidence in the humanities. | active | 7thWeek_3 | after 7thWeek_2 | 2d
Instruction: Revising your evidence. | active | 7thWeek_4 | after 7thWeek_3 | 3d
Exercise: Discussing evidence in your field. | active | 7thWeek_a | after 6thWeek_c | 2d
Exercise: Revisiting your evidence. | active | 7thWeek_b | after 7thWeek_a | 2d
Exercise: Shaping your evidence around your argument. | active | 7thWeek_c | after 7thWeek_b | 3d
Opening and Concluding Your Article | critical | 8thWeek_0 | after 7thWeek_0 | 7d
Instruction: On the importance of openings. | active | 8thWeek_1 | after 7thWeek_5 | 2d
Instruction: Revising your opening and conclusion. | active | 8thWeek_2 | after 8thWeek_1 | 2d
Exercise: Revising your title. | active | 8thWeek_a | after 7thWeek_c | 1d
Exercise: Revising your introduction. | active | 8thWeek_b | after 8thWeek_a | 1d
Exercise: Revisiting your abstract, related literature review, and author order. | active | 8thWeek_c | after 8thWeek_b | 1d
Exercise: Revising your conclusion. | active | 8thWeek_d | after 8thWeek_c | 1d
Giving, Getting, and Using Others' Feedback | critical | 9thWeek_0 | after 8thWeek_0 | 7d
Instruction: Types of feedback. | active | 9thWeek_1 | after 8thWeek_2 | 2d
Instruction: Exchanging your articles. | active | 9thWeek_2 | after 9thWeek_1 | 2d
Exercise: Sharing your article and getting feedback. | active | 9thWeek_a | after 8thWeek_d | 1d
Exercise: Making a list of remaining tasks. | active | 9thWeek_b | after 9thWeek_a | 1d
Exercise: Revising your article according to feedback. | active | 9thWeek_c | after 9thWeek_b | 1d
Editing Your Sentences | critical | 10thWeek_0 | after 9thWeek_0 | 7d
Instruction: On taking the time. | active | 10thWeek_1 | after 9thWeek_2 | 1d
Instruction: Types of revising. | active | 10thWeek_2 | after 10thWeek_1 | 1d
Instruction: The rules of editing. | active | 10thWeek_3 | after 10thWeek_2 | 1d
Instruction: The Belcher diagnostic test. | active | 10thWeek_4 | after 10thWeek_3 | 2d
Instruction: Editing your article. | active | 10thWeek_5 | after 10thWeek_4 | 2d
Exercise: Running the Belcher diagnostic test. | active | 10thWeek_a | after 9thWeek_c | 2d
Exercise: Revising your article with the diagnostic test. | active | 10thWeek_b | after 10thWeek_a | 3d
Exercise: Correcting other types of problem sentences. | active | 10thWeek_c | after 10thWeek_b | 2d
Wrapping up Your Article | critical | 11thWeek_0 | after 10thWeek_0 | 7d
Instruction: On the perils of perfection. | active | 11thWeek_1 | after 10thWeek_5 | 1d
Instruction: Finalizing your article. | active | 11thWeek_2 | after 11thWeek_1 | 2d
Instruction: The rules of editing. | active | 11thWeek_3 | after 11thWeek_2 | 1d
Instruction: The Belcher diagnostic test. | active | 11thWeek_4 | after 11thWeek_3 | 2d
Instruction: Editing your article. | active | 11thWeek_5 | after 11thWeek_4 | 1d
Exercise: Running the Belcher diagnostic test. | active | 11thWeek_a | after 10thWeek_c | 2d
Exercise: Revising your article with the diagnostic test. | active | 11thWeek_b | after 11thWeek_a | 3d
Exercise: Correcting other types of problem sentences. | active | 11thWeek_c | after 11thWeek_b | 2d
Sending Your Article | critical | 12thWeek_0 | after 11thWeek_0 | 7d
Instruction: On the importance of finishing. | active | 12thWeek_1 | after 11thWeek_5 | 2d
Instruction: Getting the submission ready. | active | 12thWeek_2 | after 12thWeek_1 | 5d
Exercise: Writing the cover letter. | active | 12thWeek_a | after 11thWeek_c | 1d
Exercise: Preparing illustrations. | active | 12thWeek_b | after 12thWeek_a | 2d
Exercise: Putting your article into the journal's style. | active | 12thWeek_c | after 12thWeek_b | 1d
Exercise: Preparing the final print or electronic version. | active | 12thWeek_d | after 12thWeek_c | 2d
Exercise: Send and celebrate! | active | 12thWeek_e | after 12thWeek_d | 1d
Responding to Journal Decisions | critical | XthWeek_0 | after 12thWeek_0 | 7d
Instruction: An exhortation. | active | XthWeek_1 | after 12thWeek_2 | 1d
Instruction: Waiting for the journal's decision. | active | XthWeek_2 | after 12thWeek_1 | 1d
Instruction: Reading the journal's decision. | active | XthWeek_3 | after XthWeek_2 | 1d
Instruction: Types of journal decisions. | active | XthWeek_4 | after XthWeek_3 | 2d
Instruction: Responding to journal decisions. | active | XthWeek_5 | after XthWeek_4 | 2d
Exercise: Evaluating and responding to the journal decision. | active | XthWeek_a | after 12thWeek_e | 7d
Exercise: Planning your revision. | active | XthWeek_b | after XthWeek_a | 2d
Exercise: Revising your article. | active | XthWeek_c | after XthWeek_b | 7d
Exercise: Drafting your revision cover letter. | active | XthWeek_d | after XthWeek_c | 2d
Exercise: Requesting permissions. | active | XthWeek_e | after XthWeek_d | 3d
Exercise: On the importance of persevering. | active | XthWeek_f | after XthWeek_e | 1d